## Cover Sheet
BILLING 8.8 TEST SCRIPTS
Powered by ProvenCourseSM
<Project Name> <Client Name> or Logo R²i For PeopleSoft Who The Document Was Prepared For Date Document Number Document Version Disposition {Draft/Final}

## Authors
<CLIENT>
Billing 8.8 Configuration Checklist
2026-07-31 05:03
This document was prepared by:
| John Doe, Senior Manager |  |  | John Doe, Senior Manager | John Doe, Senior Manager
| BearingPoint, Inc. |  |  | BearingPoint, Inc. | BearingPoint, Inc.
| 1676 International Drive |  |  | 1677 International Drive | 1678 International Drive
| McLean, VA 22102 |  |  | McLean, VA 22103 | McLean, VA 22104
| T: 703-747-3000 |  |  | T: 703-747-3001 | T: 703-747-3002
| F: 703-747-3000 |  |  | F: 703-747-3001 | F: 703-747-3002
| jdoe@bearingpoint.com |  |  | jdoe@bearingpoint.com | jdoe@bearingpoint.com
| Date | Document Version | Document Revision Description |  |  | Document Author
| Approval Date | Approved Version | Approver Role |  |  | Approver
This document is protected under the copyright laws of the United States and other countries as an unpublished work. This document contains information that is proprietary and confidential to BearingPoint, Inc. or its technical alliance partners, which shall not be disclosed outside or duplicated, used, or disclosed in whole or in part for any purpose other than to evaluate BearingPoint, Inc. Any use or disclosure in whole or in part of this information without the express written permission of BearingPoint, Inc. is prohibited.
All rights reserved. Rapid Return on Investment is a component of BearingPoint's ProvenCourse(SM) delivery framework; R2i is a registered trademark and R2i Rapid Return on Investment is a service mark of BearingPoint, Inc. and its affiliates in some countries.

## Introduction
INTRODUCTION
This document contains the test script for PeopleSoft Billing 8.8. This is intended to be used as an information gathering tool as it pertains to implementing Billing 8.8. <A brief overview of the project should be included here. Make sure to list tasks, accomplishments, and any foreseeable problems that might occur.>
Instructions The scripts need to be adapted to the client based on the client's business and PeopleSoft setup. 1. Review with the client their Billing business processes. Determine which processes will be tested. 2. Update the appropriate business processes and test scenarios in the test script spreadsheet. 3. Determine pool of employees that will be used for testing. Also, define data for new employees to be added via the hire process. 4. Determine the cycle and appropriate order of the testing of the business processes. 5. Determine the expected results for each of the test scenarios. Update the test script spreadsheet. 6. Determine who will be responsible for testing each of the scenarios and update the spreadsheet. 7. Expand business processes, where appropriate for the PeopleSoft applications implemented within the Billing module.
a. The Test Scripts tab provides the detail test scripts.
b. This spreadsheet is intended to cover the testing of typically used product features in Version 8.8 and will not be all inclusive.
c. Changes, additions and deletions to these documents are anticipated at each client engagement and time to complete necessary changes should be included in the project plan. Typical tasks that may be required include:
- Adding test data appropriate to the client (always required)
- Adding test cases to create more data
- Excluding test cases for features included that will not be used at the client site
- Adding test cases for features not included in the plan but used at the client site
- Adding test cases related to local customizations or data loads
Changes to these templates can easily be accomplished by starting with the test case sheet and then modifying the Script, then the Scenario if necessary. Changes can be made starting at the Scenario level but the changes will become increasingly complicated as you move to the next level of detail.
d. During the testing, all results are to be documented on the appropriate Application Test Scripts.
e. Also needed:
List of reports currently run.
Verify Interfaces.
Determine Sample size for conversion verification.
Determine converted table to be verified.
Define user team and responsibilities.
Create system test plan for interfaces
Ask for a copy of the current business process documentation.
Define end user training plan.
Determine training material requirements.
1.1. Purpose
<Define the purpose of the Test Cases document. Typically, this is a brief statement that indicates the overall goal of the Test Cases document,
i.e. to verify that test cases map to business requirements, etc.>
1.2. Approach
<Provide a brief summary of the approach being used to design test cases. Reference the specific business requirements document
and any other documentation used to create the test cases.>
1.3. Scope Definition
<Provide the In Scope and Out of Scope list for the Test Cases.>
1.3.1. In Scope
<Identify areas within scope based on the business requirements and design documentation. This section may be presented in bullet points.>
This is the subsection text…
1.3.2. Out of Scope
<Clearly list areas that are outside of scope based on business requirements and design documentation.>
This is the subsection text…
1.4. Constraints
<List constraints specific to the test cases for this project, such as resource constraints, testing tool constraints, etc.>
1.5. Assumptions
<List any assumptions specific to the test cases.>

## Test Scripts
Test Case Process | Control ID | Test Case | Navigational Path | Component | User ID | Prereq. | Input Data | Expected Results | Actual Results | Owner | Due Date | Comments/Status
1.1 Entering Online Invoices
| BI-0101 | Add a one-line invoice | Billing > Maintain Bills > Standard Billing | BI_ENTRY |  |  | Invoice with one line of data | Added item successfully. An Invoice Number should be assigned upon saving
| BI-0102 | Add a one-line invoice, generating accounting entries for review | Billing > Maintain Bills > Standard Billing | BI_ENTRY |  |  | Invoice with one line of data | Added item successfully. Accounting entries available for review. An Invoice Number should be assigned upon saving
| BI-0103 | Add a multi-line invoice | Billing > Maintain Bills > Standard Billing | BI_ENTRY |  |  | Invoice with multiple lines of data | Added item successfully. An Invoice Number should be assigned upon saving
| BI-0104 | Add a multi-line invoice, generating accounting entries for review | Billing > Maintain Bills > Standard Billing | BI_ENTRY |  |  | Invoice with multiple lines of data | Added item successfully. Accounting entries available for review. An Invoice Number should be assigned upon saving
| BI-0105 | Add a one-line invoice for an Inactive customer | Billing > Maintain Bills > Standard Billing | BI_ENTRY |  |  | Invoice with one line of data | Failed due to Inactive status of customer. Error message
| BI-0106 | Add a one-line invoice with discount/surcharge | Billing > Maintain Bills > Standard Billing | BI_ENTRY |  |  | Invoice with one line of data, discount/surcharge information | Added item successfully. An Invoice Number should be assigned upon saving
| BI-0107 | Add a multi-line invoice with discount/surcharge | Billing > Maintain Bills > Standard Billing | BI_ENTRY |  |  | Invoice with multiple lines of data, discount/surcharge information | Added item successfully. An Invoice Number should be assigned upon saving
1.2 Entering Consolidated Invoices
| BI-0201 | Create a consolidated bill header | Billing > Maintain Bills > Create Consolidated Header | BI_CONS_HDR |  |  | Invoice header information | Created consolidated bill header. An Invoice Number should be assigned upon saving
| BI-0202 | Attach a bill to a consolidated bill header | Billing > Maintain Bills > Attach and Detach Bills | BI_CONS_ATTACH |  |  | Identifying information for bill | Attached bill to consolidated bill header.Recall consolidated bill after saving
| BI-0203 | Detach a bill from a consolidated bill header | Billing > Maintain Bills > Attach and Detach Bills | BI_CONS_ATTACH |  |  | Identifying information for bill | Detached bill from consolidated bill header. Recall consolidated bill after saving
| BI-0204 | Attach multiple bills to a consolidated bill header | Billing > Maintain Bills > Attach and Detach Bills | BI_CONS_ATTACH |  |  | Identifying information for bills | Attached bills to consolidated bill headers. Recall consolidated bill after saving
| BI-0205 | Detach multiple bills from a consolidated bill header | Billing > Maintain Bills > Attach and Detach Bills | BI_CONS_ATTACH |  |  | Identifying information for bills | Detached bills from consolidated bill headers. Recall consolidated bill after saving
1.3 Entering Installment Bills
| BI-0301 | Add a template invoice with an installment plan of equal installments | Billing > Maintain Bills > Standard Billing Billing > Maintain Bills > Installment Bill Schedules | BI_ENTRY and BI_INST_SCHED |  |  | Invoice information, installment plan details | Added invoice with installment plan of equal installments successfully. An Invoice Number should be assigned upon saving. Receall bill after saving.
| BI-0302 | Add a template invoice with an installment plan of percentage installments | Billing > Maintain Bills > Standard Billing Billing > Maintain Bills > Installment Bill Schedules | BI_ENTRY and BI_INST_SCHED |  |  | Invoice information, installment plan details | Added invoice with installment plan of percentage installments successfully.
| BI-0303 | Add a template invoice with a custom installment plan | Billing > Maintain Bills > Standard Billing Billing > Maintain Bills > Installment Bill Schedules | BI_ENTRY and BI_INST_SCHED |  |  | Invoice information, installment plan details | Added invoice with custom installment plan successfully. An Invoice Number should be assigned upon saving. Receall bill after saving.
| BI-0304 | Create a new Generate Installment Bill process request | Billing > Maintain Bills > Create Installment Bills | RUN_BI_INSTALLMENT |  |  | Identifier for new run control | Created new run control without errors.
| BI-0305 | Run the Generate Installment Bill process | Billing > Maintain Bills > Create Installment Bills | RUN_BI_INSTALLMENT |  |  | Identifier of new run control | The Generate Installment Bill process ran without errors. Process Monitor
| BI-0306 | View messages created during the Generate Installment Bill Process | Billing > Maintain Bills > Create Installment Bills | RUN_BI_INSTALLMENT |  |  | Identifier of new run control | Viewed messages from Generate Installment Bill process successfully. Message Log, Process Monitor
1.4 Adjusting Bills
| BI-0401 | Reverse an original invoice | Billing > Maintain Bills > Adjust Entire Bill | CREATE_ADJ_BILL |  |  | Identifying information for bill | Reversed an original invoice. Inquire on invoice
| BI-0402 | Credit an entire bill and rebill with correct information | Billing > Maintain Bills > Adjust Entire Bill | CREATE_ADJ_BILL |  |  | Identifying information for bill, correct bill information | Credited an entire bill and rebill with correct information. Inquire on invoice
| BI-0403 | Adjust one bill line for an existing bill | Billing > Maintain Bills > Adjust Selected Bill Lines | CREATE_ADJ_LINE |  |  | Identifying information for bill, correct bill line information | Adjusted one bill line for an existing bill. Recall bill after saving
| BI-0404 | Adjust multiple lines for an existing bill | Billing > Maintain Bills > Adjust Selected Bill Lines | CREATE_ADJ_LINE |  |  | Identifying information for bill, correct bill line information | Adjusted multiple lines for an existing bill. Recall bill after saving
1.5 Entering Deferred Revenue Bills
| BI-0501 | Add a one-line invoice with deferred revenue parameters | Billing > Maintain Bills > Standard Billing | BI_ENTRY |  |  | Invoice with one line of data, deferred revenue parameters | Added item successfully. An Invoice Number should be assigned upon saving
| BI-0502 | Add a one-line invoice with deferred revenue parameters, generating accounting entries for review | Billing > Maintain Bills > Standard Billing | BI_ENTRY |  |  | Invoice with one line of data, deferred revenue parameters | Added item successfully. Accounting entries available for review. An Invoice Number should be assigned upon saving
| BI-0503 | Add a multi-line invoice with deferred revenue parameters | Billing > Maintain Bills > Standard Billing | BI_ENTRY |  |  | Invoice with multiple lines of data, deferred revenue parameters | Added item successfully. An Invoice Number should be assigned upon saving
| BI-0504 | Add a multi-line invoice with deferred revenue parameters, generating accounting entries for review | Billing > Maintain Bills > Standard Billing | BI_ENTRY |  |  | Invoice with multiple lines of data, deferred revenue parameters | Added item successfully. Accounting entries available for review. An Invoice Number should be assigned upon saving
| BI-0505 | Add a one-line invoice with deferred revenue parameters for an Inactive customer | Billing > Maintain Bills > Standard Billing | BI_ENTRY |  |  | Invoice with one line of data, deferred revenue parameters | Failed due to Inactive status of customer. Error message
| BI-0506 | Add a one-line invoice with deferred revenue parameters with discount/surcharge | Billing > Maintain Bills > Standard Billing | BI_ENTRY |  |  | Invoice with one line of data, discount/surcharge information, deferred revenue parameters | Added item successfully. An Invoice Number should be assigned upon saving
| BI-0507 | Add a multi-line invoice with deferred revenue parameters with discount/surcharge | Billing > Maintain Bills > Standard Billing | BI_ENTRY |  |  | Invoice with multiple lines of data, discount/surcharge information, deferred revenue parameters | Added item successfully. An Invoice Number should be assigned upon saving
1.6 Entering Recurring Bills
| BI-0601 | Create a recurring bill template | Billing > Maintain Bills > Standard Billing | BI_ENTRY |  |  | Invoice information | Created recurring bill template. An Invoice Number should be assigned upon saving. Receall bill after saving.
| BI-0602 | Define a time period for a recurring bill | Billing > Maintain Bills> Recurring Bill Schedules | BI_SCHEDULE |  |  | Time period for recurrence setting | Defined time period for recurring bill. An Invoice Number should be assigned upon saving. Receall bill after saving.
| BI-0603 | Create a new Generate Recurring Bill process request | Billing > Maintain Bills > Create Recurring Bills | RUN_BI_RECURING |  |  | Identifier for new run control | Created new run control without errors.
| BI-0604 | Run the Generate Recurring Bill process | Billing > Maintain Bills > Create Recurring Bills | RUN_BI_RECURING |  |  | Identifier of new run control | The Generate Recurring Bill process ran without errors. Process Monitor
| BI-0605 | View messages created during the Generate Recurring Bill Process | Billing > Maintain Bills > Create Recurring Bills | RUN_BI_RECURING |  |  | Identifier of new run control | Viewed messages from Generate Recurring Bill process successfully. Message Log, Process Monitor
1.7 Processing Unbilled Revenue Accruals
| BI-0701 | Create a new Load GL - Unbilled Revenue Accrual process request | Billing > Generate Invoices > Accrue Unbilled Activity > Non-Consolidated Bills Billing > Generate Invoices > Accrue Unbilled Activity > Consolidated Bills | RUN_BI_ACCRUAL or RUN_BI_ACCRUAL_CON |  |  | Identifier for new run control | Created new run control without errors.
| BI-0702 | Run the Load GL - Unbilled Revenue Accrual process | Billing > Generate Invoices > Accrue Unbilled Activity > Non-Consolidated Bills Billing > Generate Invoices > Accrue Unbilled Activity > Consolidated Bills | RUN_BI_ACCRUAL or RUN_BI_ACCRUAL_CON |  |  | Identifier of new run control | The Load GL - Unbilled Revenue Accrual process ran without errors. Process Monitor
| BI-0703 | View messages created during the Load GL - Unbilled Revenue Accrual Process | Billing > Generate Invoices > Accrue Unbilled Activity > Non-Consolidated Bills Billing > Generate Invoices > Accrue Unbilled Activity > Consolidated Bills | RUN_BI_ACCRUAL or RUN_BI_ACCRUAL_CON |  |  | Identifier of new run control | Viewed messages from Load GL - Unbilled Revenue Accrual process successfully. Message Log, Process Monitor
1.8 Processing Bills
| BI-0801 | Run a process to finalize invoice and complete subsequent integration steps. | Billing > Generate Invoices > Non-Consolidated > Single Action Invoice Billing > Generate Invoices > Consolidated > Single Action Consolidation | SNGL_ACTION or CON_SNGL_ACTION |  |  | Run a process to finalize invoice and complete subsequent integration steps.
| BI-0802 | Print preliminary copies of selected invoices | Billing > Generate Invoices > Non-Consolidated > Print Pro Forma Billing > Generate Invoices > Consolidated > Print Consolidated Pro Forma | PROFORMA or CON_PROFORMA |  |  | Print preliminary copies of selected invoices
| BI-0803 | Create a new Bill Finalization process request | Billing > Generate Invoices > Non-Consolidated > Finalize and Print Invoices Billing > Generate Invoices > Consolidated > Finalize and Print Invoices | FINAL_PRINT or CON_FINAL_PRINT |  |  | Identifier for new run control | Created new run control without errors.
| BI-0804 | Run the Bill Finalization process | Billing > Generate Invoices > Non-Consolidated > Finalize and Print Invoices Billing > Generate Invoices > Consolidated > Finalize and Print Invoices | FINAL_PRINT or CON_FINAL_PRINT |  |  | Identifier of new run control | The Bill Finalization process ran without errors. Process Monitor
| BI-0805 | View messages created during the Bill Finalization process | Billing > Generate Invoices > Non-Consolidated > Finalize and Print Invoices Billing > Generate Invoices > Consolidated > Finalize and Print Invoices | FINAL_PRINT or CON_FINAL_PRINT |  |  | Identifier of new run control | Viewed messages from Bill Finalization process successfully. Message Log, Process Monitor
| BI-0806 | Create a new Pre-Load process request | Billing > Generate Invoices > Non-Consolidated > Pre-Load Process Billing > Generate Invoices > Consolidated > Pre-Load Process | RUN_BI_PRELD or CON_BI_PRELD |  |  | Identifier for new run control | Created new run control without errors.
| BI-0807 | Run the Pre-Load process | Billing > Generate Invoices > Non-Consolidated > Pre-Load Process Billing > Generate Invoices > Consolidated > Pre-Load Process | RUN_BI_PRELD or CON_BI_PRELD |  |  | Identifier of new run control | The Pre-Load process ran without errors. Process Monitor
| BI-0808 | View messages created during the Pre-Load process | Billing > Generate Invoices > Non-Consolidated > Pre-Load Process Billing > Generate Invoices > Consolidated > Pre-Load Process | RUN_BI_PRELD or CON_BI_PRELD |  |  | Identifier of new run control | Viewed messages from Pre-Load process successfully. Message Log, Process Monitor
| BI-0809 | Create a new Load GL process request | Billing > Generate Invoices > Non-Consolidated > Create Accounting Entries Billing > Generate Invoices > Consolidated > Create Accounting Entries | RUN_BI_LOADGL or CON_BI_LOADGL |  |  | Identifier for new run control | Created new run control without errors.
| BI-0810 | Run the Load GL process | Billing > Generate Invoices > Non-Consolidated > Create Accounting Entries Billing > Generate Invoices > Consolidated > Create Accounting Entries | RUN_BI_LOADGL or CON_BI_LOADGL |  |  | Identifier of new run control | The Load GL process ran without errors. Process Monitor
| BI-0811 | View messages created during the Load GL process | Billing > Generate Invoices > Non-Consolidated > Create Accounting Entries Billing > Generate Invoices > Consolidated > Create Accounting Entries | RUN_BI_LOADGL or CON_BI_LOADGL |  |  | Identifier of new run control | Viewed messages from Load GL process successfully. Message Log, Process Monitor
1.9 Manage Billing Worksheet
| BI-0901 | Review, update, and approve proposed billing activity | Billing > Manage Billing Worksheet > Update Billing Worksheet | BI_TMP_SEARCH |  |  | Review, update, and approve proposed billing activity
1.10 Interface Transactions
| BI-1001 | Review pending interface activity in the staging area | Billing > Interface Transactions > Review Pending Transactions | INTFC_BI_N_VW_INQ |  |  | Review pending interface activity in the staging area
| BI-1002 | Review interface activity in the staging area and correct errors | Billing > Interface Transactions > Update Pending Transactions | INTFC_BI_N_VW |  |  | Review interface activity in the staging area and correct errors
| BI-1003 | Initiate a process to prepare bills from Billing Interface pending transactions | Billing > Interface Transactions > Process Billing Interface | RUN_BI_INTFC |  |  | Initiate a process to prepare bills from Billing Interface pending transactions
| BI-1004 | Review interface activity in the staging area and correct errors | Billing > Interface Transactions > Correct Interface Errors | INTFC_BI_E_VW |  |  | Review interface activity in the staging area and correct errors
| BI-1005 | Review completed Billing interface transactions | Billing > Interface Transactions > Review Interface Completions | INTFC_BI_C_VW |  |  | Review completed Billing interface transactions