## Cover Sheet
Accounts Payable 8.8 TEST SCRIPTS
Powered by ProvenCourseSM
<Project Name> <Client Name> or Logo R²i For PeopleSoft Who The Document Was Prepared For Date Document Number Document Version Disposition {Draft/Final}

## Authors
<CLIENT>
Accounts Payable Test Script
2026-07-31 07:18
This document was prepared by:
| John Doe, Senior Manager |  |  | John Doe, Senior Manager | John Doe, Senior Manager
| BearingPoint, Inc. |  |  | BearingPoint, Inc. | BearingPoint, Inc.
| 1676 International Drive |  |  | 1677 International Drive | 1678 International Drive
| McLean, VA 22102 |  |  | McLean, VA 22103 | McLean, VA 22104
| T: 703-747-3000 |  |  | T: 703-747-3001 | T: 703-747-3002
| F: 703-747-3000 |  |  | F: 703-747-3001 | F: 703-747-3002
| jdoe@bearingpoint.com |  |  | jdoe@bearingpoint.com | jdoe@bearingpoint.com
| Date | Document Version | Document Revision Description |  |  | Document Author
| Approval Date | Approved Version | Approver Role |  |  | Approver
This document is protected under the copyright laws of the United States and other countries as an unpublished work. This document contains information that is proprietary and confidential to BearingPoint, Inc. or its technical alliance partners, which shall not be disclosed outside or duplicated, used, or disclosed in whole or in part for any purpose other than to evaluate BearingPoint, Inc. Any use or disclosure in whole or in part of this information without the express written permission of BearingPoint, Inc. is prohibited.
All rights reserved. Rapid Return on Investment is a component of BearingPoint's ProvenCourse(SM) delivery framework; R2i is a registered trademark and R2i Rapid Return on Investment is a service mark of BearingPoint, Inc. and its affiliates in some countries.

## Introduction
INTRODUCTION
This document contains the test script for PeopleSoft Accounts Payable 8.8. This is intended to be used as an information gathering tool as it pertains to implementing Accounts Payable 8.8. <A brief overview of the project should be included here. Make sure to list tasks, accomplishments, and any foreseeable problems that might occur.>
Instructions The scripts need to be adapted to the client based on the client's business and PeopleSoft setup. 1. Review with the client their Accounts Payable business processes. Determine which processes will be tested. 2. Update the appropriate business processes and test scenarios in the test script spreadsheet. 3. Determine pool of employees that will be used for testing. Also, define data for new employees to be added via the hire process. 4. Determine the cycle and appropriate order of the testing of the business processes. 5. Determine the expected results for each of the test scenarios. Update the test script spreadsheet. 6. Determine who will be responsible for testing each of the scenarios and update the spreadsheet. 7. Expand business processes, where appropriate for the PeopleSoft applications implemented within the Accounts Payable module.
a. The test script tab provides the detail test scripts.
b. These spreadsheets are intended to cover the testing of typically used product features in Version 8.8 and will not be all inclusive.
c. Changes, additions and deletions to these documents are anticipated at each client engagement and time to complete necessary changes should be included in the project plan. Typical tasks that may be required include:
- Adding test data appropriate to the client (always required)
- Adding test cases to create more data
- Excluding test cases for features included that will not be used at the client site
- Adding test cases for features not included in the plan but used at the client site
- Adding test cases related to local customizations or data loads
Changes to these templates can easily be accomplished by starting with the test case sheet and then modifying the Script, then the Scenario if necessary. Changes can be made starting at the Scenario level but the changes will become increasingly complicated as you move to the next level of detail.
d. During the testing, all results are to be documented on the appropriate Application Test Scripts.
e. Also needed:
List of reports currently run.
Verify Interfaces.
Determine Sample size for conversion verification.
Determine converted table to be verified.
Define user team and responsibilities.
Create system test plan for interfaces
Ask for a copy of the current business process documentation.
Define end user training plan.
Determine training material requirements.

## Test Scripts
Test Case Process | Control ID | Test Case | Navigational Path | Component | User Id | Prereq. | Input Data | Expected Results | Actual Results | Owner | Due Date | Comments/Status
1.1. Create or Edit Vendor Information
| AP-0100a | Create New Vendor Information | Vendors -- >Vendor Information -- > Add/Update -- > Vendor | VNDR_ID |  |  | Note that there are the following Vendor Classifications: Supplier, Employee and Attorney. Fill in all required information on the following tabs: Identifying Information, Address, Location. | Vendor created, assigned identification number and shows on Vendor Detail Listing Report.
| AP-0100b | Create New Vendor Information | Vendors -- >Vendor Information -- > Add/Update -- > Vendor | VNDR_ID |  |  |  | Vendor ID is generated. Run Vendor Detail Listing Report.
| AP-0101 | Log Vendor Conversations | Vendors -- >Vendor Information -- > Maintain -- > Conversations | VNDR_CNVRSTN |  | AP-0100d | Record conversation details with vendors. | Conversation detail recorded.
| AP-0102 | Update Vendor Information | Vendors -- >Vendor Information -- > Add/Update -- > Vendor | VNDR_ID |  | AP-0100d |  | Vendor information is successfully saved.
| AP-0103 | Review Vendor Info | Administer Procurement -->Review Vendor Information -->Inquire |  |  |  | Fill in all required information on the following tabs: Identifying Information, Address, Location. | Revised vendor address information.
1.2. Create New or Edit Existing Vouchers
| AP-0200a | Create Regular Vouchers | Accounts Payable -->Vouchers -->Add/Update -->Regular Entry | VCHR_EXPRESS |  |  | Enter standard invoices and invoices associated with a purchase order. Fill in all required information on the following tabs: Invoice Information, Payments, Voucher Attributes. | Vouchers are successfully created, ID numbers are assigned and one Voucher has a "payment hold" status.
| AP-0200b | Review Voucher info | Administer Procurement -->Review Vendor Information -->Inquire -->Rejected Vouchers or Vendor Balance |  |  | AP-0200a
| AP-0200c | Run Voucher Register Report | Administer Procurement -- >Enter Voucher Information-- >Report-- >Voucher Register
| AP-0201a | Create Prepaid Voucher | Accounts Payable -->Vouchers -->Add/Update -->Regular Entry | VCHR_EXPRESS |  | AP-0100b | Fill in all required information on the following tabs: Invoice Information, Payments, Voucher Attributes. | Vouchers are successfully created, Prepayment Reference, ID numbers are assigned.
| AP-0201b | Review Inquiry page | Administer Procurement -- >Enter Voucher Information -- >Inquire -- >Voucher |  |  | AP-0201a
| AP-0202a | Create Quick Invoice Entry Voucher | Accounts Payable -- > Vouchers -- > Add/Update -- > Quick Invoice Entry | VCHR_QUICK_PNL |  | AP-0101 | Enter invoices on a heads-down entry page. | Voucher is successfully created.
| AP-0202b | Create Quick Invoice Entry Voucher | Accounts Payable -- > Vouchers -- > Add/Update -- > Quick Invoice Entry | VCHR_QUICK_PNL |  | AP-0202a |  | Voucher number is assigned. Run Voucher Register Report. Voucher is successfully created.
| AP-0203a | Create Asset Applicable Vouchers | Accounts Payable -- > Vouchers -- > Add/Update -- > Regular Entry | VCHR_EXPRESS |  | AP-0101 | Fill in all required information on the following tabs: Invoice Information, Payments, Voucher Attributes. | Voucher is successfully created.
| AP-0203b | Create Asset Applicable Vouchers | Accounts Payable -->Vouchers -->Add/Update -->Regular Entry | VCHR_EXPRESS |  | AP-0203a |  | Voucher Number is assigned. Run Voucher Register Report.
| AP-0203c | Review Inquiry page | Administer Procurement -- >Enter Voucher Information -- >Inquire -- >Voucher
| AP-0204 | Release Regular Voucher Hold After Posting Payment | Accounts Payable -->Vouchers -->Add/Update -->Regular Entry | VCHR_EXPRESS |  | AP-1600 |  | Run Pay cycle/Post Payment processes to ensure that a payment is not created. Run Payment Register by Payment Report. Payment was not processed. Payment Hold option is unchecked to allow payment to process during next Payment Post run.
| AP-0205a | Create Voucher Two-way Matched to a PO | Vendors -- >Vendor Information -- >Vendor Information-- > Add/Update -- > Vendor | VNDR_ID |  |  |  | Proceed to the next step AP-0205b.
| AP-0205b | Create Voucher Two-way Matched to a PO | Purchasing -->Receipts -- >Add/Update Receipts | RECV_PO |  | AP-0205a | Enter receipt information such as distributions, rejects, and asset tag Ids. | Proceed to the next step AP-0205c.
| AP-0205c | Create Voucher Two-way Matched to a PO | Accounts Payable -->Vouchers -->Add/Update -->Regular Entry | VCHR_EXPRESS |  | AP-0205b | Fill in all required information on the following tabs: Invoice Information, Payments, Voucher Attributes. | Proceed to the next step AP-0205d.
| AP-0205d | Create Voucher Two-way Matched to a PO | Accounts Payable -->Batch Processes -->Vouchers -->Matching | MTCH_RUN_CNTRL |  | AP-0205c | Compare vouchers to purchase orders and receipts for validation before payment. | Vouchers are successfully matched.
| AP-0205e | View voucher status | Administer Procurement -->Enter Voucher Information -->Inquire -->Matched Vouchers or Match Exceptions
| AP-0206a | Create Voucher 3-way Matched to PO with Use Tax | Vendors -- >Vendor Information -- >Vendor Information-- > Add/Update -- > Vendor | VNDR_ID |  | AP-0100d |  | Proceed to the next step AP-0206b.
| AP-0206b | Create Voucher 3-way Matched to PO with Use Tax | Purchasing -->Receipts -- >Add/Update Receipts | RECV_PO |  | AP-0206a |  | Proceed to the next step AP-0206c.
| AP-0206c | Create Voucher 3-way Matched to PO with Use Tax | Accounts Payable -->Vouchers -->Add/Update -->Regular Entry | VCHR_EXPRESS |  | AP-0206b | Fill in all required information on the following tabs: Invoice Information, Payments, Voucher Attributes. | Proceed to the next step AP-0206d.
| AP-0206d | Create Voucher 3-way Matched to PO with Use Tax | Accounts Payable -->Batch Processes -->Vouchers -->Matching | MTCH_RUN_CNTRL |  | AP-0206c |  | Vouchers are successfully matched.
| AP-0207e | View voucher status | Administer Procurement -->Enter Voucher Information -->Inquire --> Matched Vouchers or Matched Exceptions
| AP-0207a | Create Voucher 3-way Matched- Price Discrepancy | Vendors -- >Vendor Information -- >Vendor Information-- > Add/Update -- > Vendor | VNDR_ID |  |  |  | Proceed to the next step AP-0207b.
| AP-0207b | Create Voucher 3-way Matched-Price Discrepancy | Purchasing -->Receipts -- >Add/Update Receipts | RECV_PO |  | AP-0207a |  | Proceed to the next step AP-0207c.
| AP-0207c | Create Voucher 3-way Matched-Price Discrepancy | Accounts Payable -->Vouchers -->Add/Update -->Regular Entry | VCHR_EXPRESS |  | AP-0207b | Fill in all required information on the following tabs: Invoice Information, Payments, Voucher Attributes. | Proceed to the next step AP-0207d.
| AP-0207d | Create Voucher 3-way Matched-Price Discrepancy | Accounts Payable -->Batch Processes -->Vouchers -->Matching | MTCH_RUN_CNTRL |  | AP-0207c |  | Vouchers are successfully matched.
| AP-0207e | View voucher status | Administer Procurement -->Enter Voucher Information -->Inquire --> Matched Vouchers or Matched Exceptions
| AP-0208a | Create Voucher 4-way Matched-PO not inspected | Vendors -- >Vendor Information -- >Vendor Information-- > Add/Update -- > Vendor | VNDR_ID |  |  |  | Proceed to the next step AP-0208b.
| AP-0208b | Create Voucher 4-way Matched-PO not inspected | Purchasing -->Receipts -- >Add/Update Receipts | RECV_PO |  | AP-0208a |  | Proceed to the next step AP-0208c.
| AP-0208c | Create Voucher 4-way Matched-PO not inspected | Accounts Payable -->Vouchers -->Add/Update -->Regular Entry | VCHR_EXPRESS |  | AP-0208b | Fill in all required information on the following tabs: Invoice Information, Payments, Voucher Attributes. | Proceed to the next step AP-0208d.
| AP-0208d | Create Voucher 4-way Matched-PO not inspected | Accounts Payable -->Batch Processes -->Vouchers -->Matching | MTCH_RUN_CNTRL |  | AP-0208c |  | Vouchers are successfully matched.
| AP-0207e | View voucher status | Administer Procurement -->Enter Voucher Information -->Inquire --> Matched Vouchers or Matched Exceptions
| AP-0209a | Create Projects Applicable Voucher | Accounts Payable -->Vouchers -->Add/Update -->Regular Entry | VCHR_EXPRESS |  | AP-0100d | Fill in all required information on the following tabs: Invoice Information, Payments, Voucher Attributes. | Voucher is successfully created and Voucher number is assigned..
| AP-0209b | Review Inquiry page | Administer Procurement -- >Enter Voucher Information -- >Inquire -- >Voucher | VCHR_EXPRESS |  | AP-0209d
| AP-0210 | Create Work Batch-Group Voucher Entry (Optional) | Accounts Payable -->Control Groups -->Group Information | GRP_AP_CTL |  | AP-0210e | Fill in all required information on the following tabs: Assignment, Accounting, Vouchering Options, Vouchers, Tax Options. | Group number is assigned. Group is successfully created.
| AP-0211 | Create Regular Group Voucher-hold pymt (Optional) | Accounts Payable -->Vouchers -->Add/Update -->Regular Entry | VCHR_EXPRESS |  |  | Fill in all required information on the following tabs: Invoice Information, Payments, Voucher Attributes. | Group ID defaults on page and Voucher Number is assigned. Voucher is successfully created.
| AP-0212 | Voucher Error Correction | Accounts Payable -->Vouchers -->Maintain -- >Voucher Maintenance | VCHR_CORRECTION |  |  |  | Voucher will not have a status of "Recycle". Voucher Errors Corrected.
| AP-0213 | Selective Line Update | Accounts Payable -->Vouchers -->Maintain -- >Voucher Maintenance | VCHR_CORRECTION |  |  |  | Voucher error Corrected.
| AP-0214 | Selective Line Update-Errors | Accounts Payable -->Vouchers -->Maintain -- >Voucher Maintenance | VCHR_CORRECTION |  |  |  | Voucher error corrected.
| AP-0215 | Create Reversal Voucher | Accounts Payable -->Vouchers -->Add/Update -->Regular Entry | VCHR_EXPRESS |  |  | Fill in all required information on the following tabs: Invoice Information, Payments, Voucher Attributes.
| AP-0216 | Create Single Payment Voucher | Accounts Payable -->Vouchers -->Add/Update -->Regular Entry | VCHR_EXPRESS |  |  | Fill in all required information on the following tabs: Invoice Information, Payments, Voucher Attributes.
| AP-0217 | Create Template Voucher | Accounts Payable -->Vouchers -->Add/Update -->Regular Entry | VCHR_EXPRESS |  | AP-0100d
| AP-0218 | Voucher Deletion | Accounts Payable -->Vouchers -->Maintain -->Delete Voucher | VCHR_DELETE |  |  | Delete a saved voucher. | Voucher is successfully deleted.
| AP-0219 | Create Recurring Voucher | Purchasing -->Procurement Contracts -->Add/Update Contracts | CNTRCT_ENTRY |  |  | Add or modify contract header, line, and release information. Fill in all required information on the following tabs: Contract, Create Releases, Review Releases. | Recurring Voucher created.
| AP-0220a | Create Third Party Voucher | Accounts Payable -->Vouchers -->Add/Update -->Regular Entry | VCHR_EXPRESS |  |  | Fill in all required information on the following tabs: Invoice Information, Payments, Voucher Attributes. | Voucher ID is assigned. Third Party voucher is created.
| AP-0220b | Review Inquiry page | Administer Procurement -->Enter Voucher Information -->Inquire>
| AP-0221a | Create Journal Voucher | Accounts Payable -->Vouchers -->Add/Update -->Regular Entry | VCHR_EXPRESS |  | AP-0219 | Fill in all required information on the following tabs: Invoice Information, Payments, Voucher Attributes. | Journal Voucher created.
| AP-0221e | Review Inquiry page | Administer Procurement -->Enter Voucher Information -->Inquire -->Voucher Accounting Entries | VCHR_EXPRESS |  |  |  | Accounting Entries Corrected.
1.3. Create Adjustment Vouchers
| AP-0300a | Create Adjustment Voucher-Enter Credit or Debit | Accounts Payable -->Vouchers -->Add/Update -->Regular Entry | VCHR_EXPRESS |  |  | Fill in all required information on the following tabs: Invoice Information, Payments, Voucher Attributes. | Voucher adjusted.
| AP-0300c | Review Inquiry page | Administer Procurement -->Review Vendor Information -->Inquire -->Rejected Vouchers or Vendor Balance -->Balance
| AP-0300d | Run Voucher Register Report | Administer Procurement --> Enter Voucher Information --> Report --> Voucher Register
| AP-0301a | Create RTV Credit | Vendors -- >Vendor Information -- >Vendor Information-- > Add/Update -- > Vendor | VNDR_ID |  |  |  | Proceed to the next step AP-0301b.
| AP-0301b | Create RTV Credit | Accounts Payable -->Vouchers -->Add/Update -->Quick Invoice Entry | VCHR_QUICK_PNL |  | AP-0301a |  | Run Transaction Detail by Vendor Report. Credit successfully processed.
1.4. Create Recurring Voucher Payments
| AP-0400 | Process a Voucher for Recurring Payments | Accounts Payable -->Vouchers -->Add/Update -->Regular Entry | VCHR_EXPRESS |  |  |  | Recurring Payment Schedule established.
1.5. Voucher Edit and Build Process
| AP-0500a | Process Voucher Build Request | Accounts Payable -->Batch Processes -->Voucher Build | VCHR_BATCH_REQUEST |  |  | Build vouchers from quick invoices, EDI, and other external sources. | Voucher Built.
| AP-0500b | Review Voucher Build Request | Administer Procurement -->Create Payments -->Inquire -->Voucher Inquiry
| AP-0501a | Process Voucher Edit Request | Accounts Payable -->Vouchers -->Add/Update -->Regular Entry | VCHR_ERROR_DETL |  |  | Correct voucher batch errors or delete vouchers with errors. | Voucher Verified.
| AP-0501b | Review Voucher Edit Request | Administer Procurement -->Enter Voucher Information -->Inquire -->Voucher Edit Errors
1.6. Match Vouchers
| AP-0600a | Match Vouchers | Accounts Payable -->Batch Processes -->Vouchers -->Matching | MTCH_RUN_CNTRL |  |  |  | Vouchers Matched successfully.
| AP-0600b | Review Matching Results | Administer Procurement -->Enter Voucher Information -->Inquire -->Matched Vouchers or Match Exceptions
1.7. Approve Vouchers
| AP-0700a | Approving Vouchers | Accounts Payable -->Vouchers -->Approve -- > Approve Voucher | VCHR_APPROVE |  | AP-0501 |  | Voucher Approved. 1) Review Voucher Inquire Options. 2) Review Voucher Attributes Page. 3) Run Voucher Register Report.
| AP-0700b | Run Voucher Register Report | Administer Procurement --> Enter Voucher Information -->Report -->Voucher Register
1.8. Post Vouchers
| AP-0800a | Posting Vouchers | Accounts Payable -->Batch Processes -->Vouchers --> Voucher Posting | PST_VCHR_RQST |  | AP-0501a |  | Voucher posted successfully. 1) Review Voucher Inquire Options. 2) Review Voucher Attributes. 3) Run Posted Voucher Listing.
| AP-0800b | Run Posted Voucher Listing | Administer Procurement -->Enter Voucher Information -->Report -->Posted Voucher Listing
| AP-0800c | Unpost Voucher | Accounts Payable -->Vouchers -->Maintain --> UnPost Voucher | VCHR_UNPOST |  | AP-0800a |  | Voucher unposted successfully. 1) Review Voucher Inquire Options. 2) Run Voucher Register Report.
| AP-0800d | Review Voucher Inquire Options | Administer Procurement -->Enter Voucher Information -->Inquire -->Voucher Detailed Charges
| AP-0800e | Voucher Unpost | Accounts Payable -->Vouchers -->Maintain --> UnPost Voucher | VCHR_UNPOST |  | AP-0800a |  | Run Posted Voucher Listing. Run Voucher Register. Voucher unposted successfully.
| AP-0800f | Close Voucher | Accounts Payable -->Vouchers -->Maintain --> Close Voucher | VCHR_CLOSE |  |  |  | Voucher closed successfully. 1) Review Voucher Inquire Options. 2) Review Voucher Attributes. 3) Run Posted Voucher Listing.
| AP-0800g | Run Posted Voucher Listing | Administer Procurement -->Enter Voucher Information -->Report -->Posted Voucher Listing
1.9. Create Prepayment Vouchers
| AP-0900a | Apply Prepayment To Final Invoice | Accounts Payable -->Vouchers -->Add/Update -->Regular Entry | VCHR_EXPRESS |  | AP-0200c | Fill in all required information on the following tabs: Invoice Information, Payments, Voucher Attributes. | Prepayment applied to voucher.
| AP-0900b | Apply Prepayment To Final Voucher | Accounts Payable -->Vouchers -->Add/Update -->Regular Entry | VCHR_EXPRESS |  | AP-0900a |  | At Voucher Post: Debit Expense Credit AP Liability At Payment Post Debit AP Liability Credit Prepaid Expense.
1.10. Express Checks
| AP-1000 | Process Express Checks | Accounts Payable -->Vouchers -->Add/Update -->Regular Entry | VCHR_EXPRESS |  | AP-0100b |  | Check is created successfully.
1.11. Process Discounts
| AP-1100 | Discount Exceptions | Accounts Payable -->Vouchers -->Add/Update -->Regular Entry | VCHR_EXPRESS |  | AP-0100d |  | Run and review Voucher Register Report. Continue through pay cycle and confirm that payment reflects discount. Voucher appears as an Exception. Payment reflects a discount.
1.12. Create and Update Pay Cycles
| AP-1200 | Create and Update Pay Cycles | Accounts Payable -->Payments -- >Pay Cycle Processing -->Payment Selection Criteria | PYCYCL_DEFN |  | AP-0800a | Establish selection criteria for one or more pay cycles. Fill in all required information on the following tabs: Dates, Preferences, Source/BU, Bank/Method, Pay Group/Netting, Draft Options | Pay Cycle Information created or updated.
1.13. Pay Cycle Manager
| AP-1300a | Pay Cycle Manager Status | Accounts Payable -->Payments -->Pay Cycle Processing -->Pay Cycle Manager | PYCYCL_MGR |  | AP-1200f | Note: For Exceptions Status items such as Pay Cycle Exceptions, Lost Discounts, Conversion Alert and Withholding Alert you may pause the Pay Cycle to fix them before continuing. | Review Create Payment Inquire Options. Assessment of the Pay Cycle status processed.
| AP-1300b | Pay Cycle Manager - Create Payments | Accounts Payable -->Payments -->Pay Cycle Processing -->Pay Cycle Manager | PYCYCL_MGR |  | AP-1300a | Select, review, and create scheduled payments. | Print the Trial Register to validate the results of the payment selection and criteria.
| AP-1300c | Pay Cycle Approval | Accounts Payable -->Payments -->Pay Cycle Approvals -- > Pay Cycle | PYCYCL_APPROVAL |  | AP-1300b | Approve or deny approval for a pay cycle. | Review Pay Cycle Approval page status. Pay Cycle Approval processed successfully.
| AP-1300d | Print Checks | Accounts Payable -->Payments -->Pay Cycle Processing -->Pay Cycle Manager | PYCYCL_MGR |  | AP-1300c |  | Pay Cycle page will display a "Completed" status. Payment is executed successfully.
1.14. Restart A Pay Run
| AP-1400a | Restarting A Payment Print Run | Accounts Payable -->Payments -->Pay Cycle Processing -->Check Restart | PYCYCL_RSTRT |  |  | Restart check printing. | Checks are recreated successfully.
| AP-1400b | Produce Positive Payment Files | Accounts Payable -->Payments -->Pay Cycle Processing -->Manual Positive Payment | PYCYCL_POS_PAY |  | AP-1300d | Create a positive payment file for the bank. | Confirm payment reference is "Format Positive Pay". Positive payment file is executed.
1.15. Create and Update Pay Cycles
| AP-1500a | Process Manual Payment | Accounts Payable -->Payments -->Pay Cycle Processing -->Manual Positive Payment | PYCYCL_POS_PAY |  |  |  | Manual Check processed.
| AP-1500b | Process Manual Payment | Accounts Payable -->Vouchers -->Add/Update -->Regular Entry | VCHR_EXPRESS |  | AP-1500a |  | Manual Payment Voucher number is assigned. Manual Payment Voucher created.
1.16. Request Payment Posting
| AP-1600 | Run Payment Posting Request | Accounts Payable -->Batch Processes -->Payment -->Payment Posting | PST_PYMNT_RQST |  | AP-1300c | Request a process to post payments. | Review Process Scheduler and evaluate results. Review Create Payments Inquire Options. Run Payment Register By Payment Report. Payments Posted to the General Ledger
1.17. Cancel Payments
| AP-1700 | Place a Stop on a payment | Accounts Payable -->Payments -->Cancel/Void Payments -->Payment Cancellation | PYMNT_CANCEL |  |  | Request to cancel payments. | Review Create Payments>Inquire options Payment is stopped and voided.
1.18. Load Assets Request
| AP-1800 | Run Load Assets Request | Accounts Payable -->Batch Processes -->Extracts and Loads -->Load Assets Request | INTFC_APAM_RQST |  | AP-0800a | Populate pre-interface records for assets. | View the INTFC_PRE_AM table on the Pre-Interface Table (Pre-AM01) page. Population of the Asset Management pre-interface table, and update the AM Distribution Status on the distribution lines for the selected vouchers are D (Distributed).
1.19. Payables Open Liability
| AP-1900a | Payables Open Liability | Accounts Payable -->Reports -->Voucher Reconciliation -->Payables Open Liability | RUN_APY1406 |  |  | Run a Payables open liability report. | Run AP Open Liability Report Open Liability Requested and Table Updated
| AP-1900b | Run AP/GL Account Recon Request | Accounts Payable -->Reports -->Voucher Reconciliation -->AP/GL Account Recon Request | APGL_RECN_REQ2 |  |  | View account totals by journal and account number. | Print and Review AP/GL Account Reconciliation Report. Report reflects the Journal Line and ID totals.
| AP-1900c | Create and Update Pay Cycles | Accounts Payable -->Reports -->Voucher Reconciliation -->AP/GL Journal Recon Request | APGL_RECN_REQ1 |  |  | Create a report by journal and journal line. | Run and review the AP/GL Account Reconciliation Report. Account totals by Journal ID and Account are reported.
1.20. Define Aging Categories
| AP-2000 | Define Payables Aging | Set Up Financials/Supply Chain -->Product Related -->Procurement Options -- > Payments -- > Define Aging Categories -- > | AP_AGING_CYCLE |  | AP-1600 | Define aging categories to generate aging reports. | Run Reports: Payment Aging By Bank and/or By Vendor Aging Categories Defined
1.21. Payment Forecasting
| AP-2100a | Analyze Forecasting Information | Accounts Payable -->Reports -->Forecast -->Forecast Cycle | PYFRCST_CYCLE |  | AP-1600 |  | Proceed to the next step AP-2100b.
| AP-2100b | Run Forecast Cycle | Accounts Payable -->Reports -->Forecast -->Forecast Cycle | PYFRCST_CYCLE |  | AP-2100a |  | Proceed to the next step AP-2100c.
| AP-2100c | Run Payment Forecast Report | Accounts Payable -->Reports -->Forecast -->Forecast Cycle | PYFRCST_CYCLE |  | AP-2100b | Define forecast cycles by date range, category, and description. | Print and Review AP Payment Forecast Report. Report Created and Forecast Information Analyzed.
1.22. Process Withholdings
| AP-2200a | Create New 1099 Vendor | Vendors -- >Vendor Information -- >Vendor Information-- > Add/Update --> Vendor | VNDR_ID |  |  | Refer to AP-0101 Create New Vendor Information. | Run Vendor Detail Listing 1099 Vendor created. Proceed to next step AP-02200b.
| AP-2200b | Create 1099 Voucher | Accounts Payable -->Vouchers -->Add/Update -->Regular Entry | VCHR_EXPRESS |  | AP-2200a | Refer to Test Process 1.2 Create New or Update Existing Voucher. | Voucher Created. Proceed to the next step.
| AP-2200c | Create and Update Pay Cycles for 1099 Process | Accounts Payable -->Payments -- >Pay Cycle Processing -->Payment Selection Criteria | PYCYCL_DEFN |  | AP-2200b | Note Refer to the following Test Cases AP-12 Create and Update Pay Cycles AP-13 Pay Cycle Manager AP-16 Request Payment Posting. | Proceed to the next step AP-2200d.
| AP-2200d | Pay Cycle Manager for 1099 Process | Accounts Payable -->Payments -->Pay Cycle Processing -->Pay Cycle Manager | PYCYCL_MGR |  | AP-2200c |  | Proceed to the next step AP-2200e.
| AP-2200e | Run Withholding Calculation Report | Accounts Payable -->Reports -->Payments -->Withhold Calculation | RUN_APY7050 |  | AP-2200d | View withholding-related calculations made during the pay cycle. | Review calculation on report. Withholding Calculations created. Proceed to the next step AP-2200f.
| AP-2200f | Withholding Posting | Vendors -->1099/Global Withholdings -->Maintain -- >Post Withholdings | WTHD_TRXN_POST |  | AP-2200e | Post withholding information. | Voucher and Payment information are in transaction tables. Proceed to the next step AP-2200g.
| AP-2200g | Review Withholding Posting | Administer Procurement -->Manage Withholding -->Inquire -->Vendor Valance By Class -->Vendor Balance
| AP-2200h | Create Reporting Information | Vendors -->1099/Global Withholdings -- > Global Withholding Reports -- > Create Reporting Information | WTHD_RPT_POST |  | AP-2200f | Populate the table used to create global withholding reports. | Repot Table populated with data from the withholding transaction table. Proceed to the next step AP-2200h.
| AP-2200i | Run Withholding Report | Set Up Financials/Supply Chain -->Product Related -->Procurement Options -- > Withholding -- > Withholding Report Information | WTHD_RPT_PNG |  | AP-2200h | Review withholding report information. | Withholding Report generated with information.
| AP-2200j | Review Withholding Report | Administer Procurement -->Manage Withholdings -->Inquire -->Withholding Report Info
1.23. Journal Generator-Transfer Payables to General Ledger
| AP-2300a | Transfer AP invoices only to GL | General Ledger -->Journals -->Subsystem Journals -->Generate Journals | JRNLGEN_REQUEST |  | AP-1600 |  | AP Invoice journal entries created.
| AP-2300b | Review Transfer | Administer Procurement -->Enter Voucher Information -->Inquire -->Journal Drill Down and/or Voucher Accounting Entries
| AP-2300c | Transfer AP payments only to GL | General Ledger -->Journals -->Subsystem Journals -->Generate Journals | JRNLGEN_REQUEST |  | AP-1600 |  | AP Payment journal entries created.
| AP-2300d | Review Transfer | Administer Procurement -->Enter Voucher Information -->Inquire -->Journal Drill Down and/or Voucher Accounting Entries
1.24. Accounts Payable Reports and Analysis Tools
| AP-2400 | Run Payables Reports | Refer to Payables Reports List |  |  |  |  | Review of the standard delivered Payables Reports.
| AP-2401 | Run Payables Open Liability Report | Accounts Payable -->Reports -->Voucher Reconciliation -->Payables Open Liability | RUN_APY1406 |  |  | Open Liability Report (APY 1406) & Unrecorded Liability Report (APY 1407) are now combined under this report.
| AP-2402 | Run Vendor Liability Aging Report | Accounts Payable -->Reports -->Voucher Reconciliation -->Vendor Liability Aging | RUN_APY1408 |  |  | Aged Vendor Liability (APY 1408) & Vendor Aging Report (APY 1430) are now combined under this report.
| AP-2403 | Match Status Chart | Accounts Payable -->Review Accounts Payable Info -->Vouchers -->Match Manager | MATCH_MGR |  |  |  | Shows vouchers by match exception status for a business unit over a specified period of time.
| AP-2404 | Pay Cycle Summary Chart | Accounts Payable -->Review Accounts Payable Info -->Payments -->Pay Cycle Summary Metric | MTRC_AP_PYCYCL |  |  |  | Shows the monetary amount that was paid in a pay cycle from each bank account and payment method combination.
| AP-2405 | Payment Inquiry Chart | Accounts Payable -->Review Accounts Payable Info -->Payments -->Payment | PYMNT_INQ_SRCH |  |  |  | Shows the monetary amount that was paid, by currency and payment method, over a specified period of time and meeting other search criteria that you can enter.
| AP-2406 | Scheduled Due Aging Chart | Accounts Payable -->Review Accounts Payable Info -->Vendor -->Scheduled Due Aging Metric | MTRC_AP_SCHD_AGING |  |  |  | Shows the total monetary amount scheduled due, by voucher status and aging time period.
| AP-2407 | Past Due Aging Chart | Accounts Payable -->Review Accounts Payable Info -->Vendor -->Past Due Aging Metric | MTRC_AP_PAST_AGING |  |  |  | Shows the total monetary amount past due, by voucher status and aging time period.